## Defect Tracking
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Member 1 | 01-09-2026 | Face detection was not working when the camera permission was denied. | 1 | Member 2 | Functional | Added camera permission validation and user notification. | 02-09-2026 | Closed | Camera permission is now handled correctly.
2 | Member 2 | 03-09-2026 | Candidate photo was not being stored correctly after capture. | 1 | Member 1 | Data | Fixed image storage path and database record handling. | 04-09-2026 | Closed | Photo is stored successfully.
3 | Member 3 | 05-09-2026 | Face absence event was not recorded when the candidate moved away from the camera. | 2 | Member 1 | Functional | Updated face-presence detection and event logging logic. | 06-09-2026 | Closed | Face absence is now logged.
4 | Member 1 | 06-09-2026 | Multiple faces were not detected correctly during monitoring. | 2 | Member 2 | Functional | Improved multiple-face detection logic using OpenCV. | 08-09-2026 | Closed | Multiple-face events are recorded.
5 | Member 4 | 08-09-2026 | Browser tab switching was not being recorded in some cases. | 2 | Member 3 | Functional | Updated browser activity logging mechanism. | 09-09-2026 | Closed | Tab-switch events are now logged.
6 | Member 2 | 09-09-2026 | Suspicious events were being recorded without proper timestamps. | 2 | Member 3 | Data | Added timestamp generation while storing events. | 10-09-2026 | Closed | Timestamps are now stored correctly.
7 | Member 5 | 10-09-2026 | Integrity score was not calculated when there were no suspicious events. | 3 | Member 4 | Calculation | Added default event handling and corrected score calculation logic. | 11-09-2026 | Closed | Score is generated for all sessions.
8 | Member 1 | 11-09-2026 | Integrity score was displayed outside the expected range. | 3 | Member 4 | Calculation | Normalized the integrity score to the defined range. | 12-09-2026 | Closed | Score is now normalized correctly.
9 | Member 3 | 12-09-2026 | Risk classification was incorrect for some integrity scores. | 3 | Member 5 | Logic | Corrected the risk-level threshold conditions. | 13-09-2026 | Closed | Risk categories are assigned correctly.
10 | Member 4 | 13-09-2026 | RAG system failed to retrieve relevant information from some reviews. | 3 | Member 5 | Functional | Improved document preprocessing and retrieval configuration. | 14-09-2026 | Closed | Review retrieval improved.
11 | Member 2 | 14-09-2026 | RAG-generated report was not displayed correctly in the UI. | 3 | Member 3 | UI | Fixed API response handling and UI rendering. | 15-09-2026 | Closed | Report is displayed correctly.
12 | Member 5 | 15-09-2026 | Dashboard charts were not updated after new exam sessions were completed. | 4 | Member 2 | UI | Updated dashboard data-refresh logic. | 16-09-2026 | Closed | Charts now reflect updated data.
13 | Member 1 | 15-09-2026 | Event frequency chart displayed incorrect values for some sessions. | 4 | Member 4 | Data | Corrected event aggregation and chart calculation. | 16-09-2026 | Closed | Event counts are accurate.
14 | Member 3 | 16-09-2026 | Unauthorized users could access the manager dashboard URL. | 5 | Member 2 | Security | Added role-based access control for manager dashboard. | 17-09-2026 | Closed | Unauthorized access is now blocked.
15 | Member 5 | 17-09-2026 | AI integrity report generation takes longer for sessions with large event logs. | 5 | Member 4 | Performance | Optimized event preprocessing and report generation. | 17-09-2026 | Open | Performance improvement is still being tested.