## Sprint Backlog
Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | US01 | Study online examination workflows and define system architecture and database schema. | Must Have | — | Member 1 | 3 - Completed
1 | US02 | Set up Flask application structure, SQLite database, and candidate authentication with session lifecycle management. | Must Have | US01 | Member 2 | 3 - Completed
1 | US03 | Implement candidate photo capture at registration using OpenCV. | Must Have | US02 | Member 1 | 3 - Completed
1 | US04 | Build a synthetic session log data generator using Faker for testing. | Should Have | US02 | Member 3 | 3 - Completed
2 | US05 | Implement Haar Cascade based face presence monitoring and log face-absent intervals with timestamps. | Must Have | US03 | Member 1 | 3 - Completed
2 | US06 | Build browser activity and event logging for focus loss, tab switching, and session interactions. | Must Have | US02 | Member 2 | 3 - Completed
2 | US07 | Develop a rule-based suspicious event detection engine with configurable thresholds. | Must Have | US05, US06 | Member 3 | 3 - Completed
2 | US08 | Validate face detection reliability and event logging accuracy across varied test scenarios. | Should Have | US05, US06, US07 | Member 4 | 3 - Completed
3 | US09 | Build the integrity scoring module using Pandas with weighted event scoring and face presence ratio calculation. | Must Have | US07 | Member 3 | 3 - Completed
3 | US10 | Implement normalized risk labelling based on integrity scores. | Must Have | US09 | Member 3 | 3 - Completed
3 | US11 | Develop analytics for integrity score distribution and event frequency using Pandas, Matplotlib, and Seaborn. | Must Have | US09 | Member 4 | 3 - Completed
3 | US12 | Implement K-Means session clustering and cohort risk profiling using Scikit-learn. | Should Have | US09, US11 | Member 4 | 3 - Completed
3 | US13 | Validate scoring consistency and analytics outputs using synthetic session data. | Should Have | US09, US11, US12 | Member 5 | 3 - Completed
4 | US14 | Implement a LangChain-based AI integrity report agent connected to session event logs and integrity scores. | Must Have | US09, US10 | Member 5 | 3 - Completed
4 | US15 | Test the AI integrity report agent with low, medium, and high-risk session profiles. | Must Have | US14 | Member 5 | 3 - Completed
4 | US16 | Build alert and evidence management for suspicious events, including secure screenshot and incident-log storage in SQLite. | Must Have | US07 | Member 2 | 3 - Completed
4 | US17 | Validate AI-generated summaries for clarity, accuracy, and usefulness to invigilators. | Should Have | US14, US15 | Member 1 | 3 - Completed